## Sheet1
Fitting power supply Voltage: 8.5 V |  |  |  |  | Fitting Range: 19800 - 45800 |  |  |  |  | Fitting interval: 1000
Fitting Max: +/- 7.5 A |  |  |  |  | Fitting test point number: 27 |  |  |  |  | Fitting precision: 0.01 V
*Channel needs to be redone if labeled red
Board# | Board 1 |  | Board 2 |  | Board 3 |  | Board 4 |  | Board 5 |  | Board 6 |  | Board 7 |  |  | Code updated date
Date updated | 2016-08-18 |  | 2016-08-20 |  | 2016-08-18 |  | 2016-08-22 |  | 2016-08-19 |  | 2016-08-19 |  | 2016-08-20 |  |  |  | Monitior |  | Control
Fitting item | Control | Monitor | Control | Monitor | Control | Monitor | Control | Monitor | Control | Monitor | Control | Monitor | Control | Monitor |  | Board1 |  |  | 2016-08-18
CH A | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ |  | Board2 | 2016-08-22 |  | 2016-08-22
CH B | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ |  | Board3 |  |  | 2016-08-20
CH C | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ |  | Board4 | 2016-08-22 |  | 2016-08-22
CH D | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ |  | Board5 | 2016-08-22 |  | 2016-08-22
CH E | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ |  | Board6 | 2016-08-22 |  | 2016-08-22
CH F | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ |  | Board7 | 2016-08-22 |  | 2016-08-22
CH G | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √
CH H | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √
CH I | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √
CH J | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √ | √
| Needs to be redone |  |  |  | Needs to be redone | [7 empty] | Need to add "19800"
Channel location |  | Problems Encountered |  |  | Problem Date |  | Probable Cause |  |  |  | Solution |  |  |  | Fixed? | Fixed Date |  | Note
Board 4 CHB |  | No monitor data |  |  | 2016-08-19 |  | Monitor resistor burned |  |  |  | Reinforce pin connection |  |  |  | √ | 2016-08-22 |  | Need to redo monitor fitting after fix
Board 4 CHG |  | Output degenerates overtime |  |  | 2016-08-19 |  | Loose OPA connection? |  |  |  | Replace with a new OPA |  |  |  | √ | 2016-08-22 |  | Need to redo control fitting for that CH
Board5 CHF |  | Monitor data not correct |  |  | 2016-08-20 |  | Monitor resistor burned |  |  |  | Resolder Monitor resistor |  |  |  | √ |  |  | Need to redo monitor fitting after fix
Board5 CHG |  | Monitor data not correct |  |  | 2016-08-20 |  | Monitor resistor burned |  |  |  | Resolder Monitor resistor |  |  |  | √ |  |  | Need to redo monitor fitting after fix
Board 7 CHA,F-J |  | Negtive current has MAX limit |  |  | 2016-08-20 |  | ???? |  |  |  | ???? | [6 empty] | Need to add control/monitor fitting for Max Neg current
Board 7 CHA-J |  | Cannot output more than -7 A |  |  | 2016-08-20 |  | Incorrect monitor resistor value |  |  |  | Replace monitor resistor | [6 empty] | Need to redo monitor fitting after fix
Board 4 CHB |  | Output degenerates overtime |  |  | 2016-08-22 |  | Fan location related (loose OPA connection) |  |  |  | Reinforce OPA surface soldering |  |  |  | √ | 2016-08-22
Note Board
1. Board 1 and 3 needs to be fitted all over again after being took down from the shelf. They were fitted under 7.5 V but we now use 8.5 V for all boards. 2. Board 7 Channel F - J uses the old version of the current monitor circuit, which cannot sense current < -7 A. The current monitor circuit for these 5 channels needs to be replaced and we need to redo the monitor citting.